## Sheet1
year | type_of_work | altername | contractor | idleft | idright | g2 | g3 | g4 | rrl | a_index | a_region | a_place | date_start | adr_prepare | tech_fin | equipment_fin | equipment_prepared | contractor_accepted | ready_for_work | params_fin | integration_fin | monitoring_fin | commisioning_fin
2023 | 1 | 20771 | 10 | 53841 | 188 | 1 | 0 | 1 | 0 | 139086 | 0 | 1 | 2022-09-12 09:34 | 2022-10-06 09:34